## Dashboard
MV/F.O Cable Terminations and Joints Handover
Infrastructure Type | Total Scope | Inspected w/ Comments | Pending | Progress %
MV-Cable Terminations | 69 | 17 | 52 | 24.64%
MV-Cable Joints | 108 | 22 | 86 | 20.37%
F.O. Terminations | 69 | 6 | 63 | 8.696%

## MV-Cable Terminations
IR-Number | WTG Number | Loop Number | Termination Status | Remarks / Notes | Pending comments
| WTG 01 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 02 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 03 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 04 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 05 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 06 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 07 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 08 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 09 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 10 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 11 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-00014 | WTG 12 | Loop 7 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 13 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-00015 | WTG 14 | Loop 8 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 15 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 16 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-0005 | WTG 17 | Loop 9 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 18 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 19 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-00013 | WTG 20 | Loop 11 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
TE-RFI-00012 | WTG 21 | Loop 11 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 22 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 23 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 24 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 25 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 26 | Loop 14 | Pending | not support available but cables has scratches. | VLF/Clamps/P.Label/Plates
| WTG 27 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-0003 | WTG 28 | Loop 15 | Inspected with comments | VLF done multi | VLF/Clamps/P.Label/Plates
TE-RFI-0008 | WTG 29 | Loop 15 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
TE-RFI-0006 | WTG 30 | Loop 16 | Inspected with comments | VLF done Multi | VLF/Clamps/P.Label/Plates
| WTG 31 | Loop 16 | Pending | Support available but Two crimps instead of three high risk. | VLF/Clamps/P.Label/Plates
TE-RFI-0004 | WTG 32 | Loop 17 | Inspected with comments | VLF done Multi | VLF/Clamps/P.Label/Plates
TE-RFI-0007 | WTG 33 | Loop 17 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
TE-RFI-0001-1 | WTG 34 | Loop 18 | Inspected with comments | VLF test done Multi | VLF/Clamps/P.Label/Plates
TE-RFI-0002 | WTG 35 | Loop 18 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 36 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 37 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 38 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 39 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 40 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-00011 | WTG 41 | Loop 21 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
TE-RFI-00010 | WTG 42 | Loop 22 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
TE-RFI-0009 | WTG 43 | Loop 22 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 44 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 45 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 46 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 47 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 48 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 49 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 50 | Loop 27 | Pending | support available but cables has scratches | VLF/Clamps/P.Label/Plates
| WTG 51 |  | Pending |  | VLF/Clamps/P.Label/Plates
TE-RFI-00016 | WTG 52 | Loop 28 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
TE-RFI-00017 | WTG 53 | Loop 28 | Inspected with comments |  | VLF/Clamps/P.Label/Plates
| WTG 54 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 55 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 56 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 57 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 58 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 59 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 60 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 61 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 62 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 63 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 64 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 65 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 66 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 67 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 68 |  | Pending |  | VLF/Clamps/P.Label/Plates
| WTG 69 |  | Pending |  | VLF/Clamps/P.Label/Plates

## MV-Cable Joints
IR-Number | Joint Number | Loop Number | Joint Status | Remarks / Notes
| MJ-01 |  | Pending | Concrete chambers and VLF
| MJ-02 |  | Pending | Concrete chambers and VLF
| MJ-03 |  | Pending | Concrete chambers and VLF
| MJ-04 |  | Pending | Concrete chambers and VLF
| MJ-05 |  | Pending | Concrete chambers and VLF
| MJ-06 |  | Pending | Concrete chambers and VLF
| MJ-07 |  | Pending | Concrete chambers and VLF
| MJ-08 |  | Pending | Concrete chambers and VLF
| MJ-09 |  | Pending | Concrete chambers and VLF
JO-RFI-00022 | MJ-10 | Loop 2 | Inspected with comments | Concrete chambers and VLF
| MJ-11 |  | Pending | Concrete chambers and VLF
| MJ-12 |  | Pending | Concrete chambers and VLF
| MJ-13 |  | Pending | Concrete chambers and VLF
| MJ-14 |  | Pending | Concrete chambers and VLF
| MJ-15 |  | Pending | Concrete chambers and VLF
| MJ-16 |  | Pending | Concrete chambers and VLF
| MJ-17 |  | Pending | Concrete chambers and VLF
| MJ-18 |  | Pending | Concrete chambers and VLF
| MJ-19 |  | Pending | Concrete chambers and VLF
| MJ-20 |  | Pending | Concrete chambers and VLF
| MJ-21 |  | Pending | Concrete chambers and VLF
| MJ-22 |  | Pending | Concrete chambers and VLF
| MJ-23 |  | Pending | Concrete chambers and VLF
| MJ-24 |  | Pending | Concrete chambers and VLF
| MJ-25 |  | Pending | Concrete chambers and VLF
| MJ-26 |  | Pending | Concrete chambers and VLF
| MJ-27 |  | Pending | Concrete chambers and VLF
| MJ-28 |  | Pending | Concrete chambers and VLF
| MJ-29 |  | Pending | Concrete chambers and VLF
| MJ-30 |  | Pending | Concrete chambers and VLF
JO-RFI-00019 | MJ-31 | Loop 6 | Inspected with comments | Concrete chambers and VLF
| MJ-32 |  | Pending | Concrete chambers and VLF
JO-RFI-00013 | MJ-33 | Loop 7 | Inspected with comments | Concrete chambers and VLF
| MJ-34 |  | Pending | Concrete chambers and VLF
| MJ-35 |  | Pending | Concrete chambers and VLF
JO-RFI-00020 | MJ-36 | Loop 7 | Inspected with comments | Concrete chambers and VLF
| MJ-37 |  | Pending | Concrete chambers and VLF
| MJ-38 |  | Pending | Concrete chambers and VLF
JO-RFI-00021 | MJ-39 | Loop 8 | Inspected with comments | Concrete chambers and VLF
| MJ-40 |  | Pending | Concrete chambers and VLF
| MJ-41 |  | Pending | Concrete chambers and VLF
| MJ-42 |  | Pending | Concrete chambers and VLF
| MJ-43 |  | Pending | Concrete chambers and VLF
| MJ-44 |  | Pending | Concrete chambers and VLF
| MJ-45 |  | Pending | Concrete chambers and VLF
| MJ-46 |  | Pending | Concrete chambers and VLF
| MJ-47 |  | Pending | Concrete chambers and VLF
| MJ-48 |  | Pending | Concrete chambers and VLF
| MJ-49 |  | Pending | Concrete chambers and VLF
JO-RFI-00012 | MJ-50 | Loop 12 | Inspected with comments | Concrete chambers and VLF
| MJ-51 |  | Pending | Concrete chambers and VLF
JO-RFI-00018 | MJ-52 | Loop 13 | Inspected with comments | Concrete chambers and VLF
| MJ-53 |  | Pending | Concrete chambers and VLF
| MJ-54 |  | Pending | Concrete chambers and VLF
| MJ-55 |  | Pending | Concrete chambers and VLF
JO-RFI-0004 | MJ-56 | Loop 14 | Inspected with comments | Concrete chambers and VLF
JO-RFI-0002 | MJ-57 | Loop 14 | Inspected with comments | Concrete chambers and VLF
JO-RFI-0001 | MJ-58 | Loop 14 | Inspected with comments | Concrete chambers and VLF
| MJ-59 |  | Pending | Concrete chambers and VLF
JO-RFI-0005 | MJ-60 | Loop 15 | Inspected with comments | Concrete chambers and VLF
JO-RFI-0003 | MJ-61 | Loop 15 | Inspected with comments | Concrete chambers and VLF
| MJ-62 |  | Pending | Concrete chambers and VLF
| MJ-63 |  | Pending | Concrete chambers and VLF
| MJ-64 |  | Pending | Concrete chambers and VLF
| MJ-65 |  | Pending | Concrete chambers and VLF
JO-RFI-00016 | MJ-66 | Loop 19 | Inspected with comments | Concrete chambers and VLF
JO-RFI-00017 | MJ-67 | Loop 19 | Inspected with comments | Concrete chambers and VLF
| MJ-68 |  | Pending | Concrete chambers and VLF
JO-RFI-00014 | MJ-69 | Loop 20 | Inspected with comments | Concrete chambers and VLF
| MJ-70 |  | Pending | Concrete chambers and VLF
| MJ-71 |  | Pending | Concrete chambers and VLF
JO-RFI-00015 | MJ-72 | Loop 21 | Inspected with comments | Concrete chambers and VLF
| MJ-73 |  | Pending | Concrete chambers and VLF
JO-RFI-0006 | MJ-74 | Loop 23 | Inspected with comments | Concrete chambers and VLF
JO-RFI-0007 | MJ-75 | Loop 23 | Inspected with comments | Concrete chambers and VLF
JO-RFI-0008 | MJ-76 | Loop 23 | Inspected with comments | Concrete chambers and VLF
| MJ-77 |  | Pending | Concrete chambers and VLF
| MJ-78 |  | Pending | Concrete chambers and VLF
| MJ-79 |  | Pending | Concrete chambers and VLF
| MJ-80 |  | Pending | Concrete chambers and VLF
| MJ-81 |  | Pending | Concrete chambers and VLF
JO-RFI-0009 | MJ-82 | Loop 28 | Inspected with comments | Concrete chambers and VLF
JO-RFI-00011 | MJ-83 | Loop 28 | Inspected with comments | Concrete chambers and VLF
| MJ-84 |  | Pending | Concrete chambers and VLF
JO-RFI-00010 | MJ-85 | Loop 29 | Inspected with comments | Concrete chambers and VLF
| MJ-86 |  | Pending | Concrete chambers and VLF
| MJ-87 |  | Pending | Concrete chambers and VLF
| MJ-88 |  | Pending | Concrete chambers and VLF
| MJ-89 |  | Pending | Concrete chambers and VLF
| MJ-90 |  | Pending | Concrete chambers and VLF
| MJ-91 |  | Pending | Concrete chambers and VLF
| MJ-92 |  | Pending | Concrete chambers and VLF
| MJ-93 |  | Pending | Concrete chambers and VLF
| MJ-94 |  | Pending | Concrete chambers and VLF
| MJ-95 |  | Pending | Concrete chambers and VLF
| MJ-96 |  | Pending | Concrete chambers and VLF
| MJ-97 |  | Pending | Concrete chambers and VLF
| MJ-98 |  | Pending | Concrete chambers and VLF
| MJ-99 |  | Pending | Concrete chambers and VLF
| MJ-100 |  | Pending | Concrete chambers and VLF
| MJ-101 |  | Pending | Concrete chambers and VLF
| MJ-102 |  | Pending | Concrete chambers and VLF
| MJ-103 |  | Pending | Concrete chambers and VLF
| MJ-104 |  | Pending | Concrete chambers and VLF
| MJ-105 |  | Pending | Concrete chambers and VLF
| MJ-106 |  | Pending | Concrete chambers and VLF
| MJ-X1 |  | Pending | Concrete chambers and VLF
| MJ-X2 |  | Pending | Concrete chambers and VLF

## F.O. Terminations
IR-Number | WTG Number | Ring / Loop Number | F.O. Termination Status | Remarks / Notes
| WTG 01 |  | Pending
| WTG 02 |  | Pending
| WTG 03 |  | Pending
| WTG 04 |  | Pending
| WTG 05 |  | Pending
| WTG 06 |  | Pending
| WTG 07 |  | Pending
| WTG 08 |  | Pending
| WTG 09 |  | Pending
| WTG 10 |  | Pending
| WTG 11 |  | Pending
| WTG 12 |  | Pending
| WTG 13 |  | Pending
| WTG 14 |  | Pending
| WTG 15 |  | Pending
| WTG 16 |  | Pending
| WTG 17 |  | Pending
| WTG 18 |  | Pending
| WTG 19 |  | Pending
| WTG 20 |  | Pending
| WTG 21 |  | Pending
| WTG 22 |  | Pending
| WTG 23 |  | Pending
| WTG 24 |  | Pending
| WTG 25 |  | Pending
| WTG 26 |  | Pending
| WTG 27 |  | Pending
| WTG 28 | Ring 4 | Inspected with comments
| WTG 29 | Ring 4 | Inspected with comments
| WTG 30 | Ring 4 | Inspected with comments
| WTG 31 |  | Pending
| WTG 32 |  | Pending
| WTG 33 | Ring 5 | Inspected with comments
| WTG 34 | Ring 5 | Inspected with comments
| WTG 35 | Ring 5 | Inspected with comments
| WTG 36 |  | Pending
| WTG 37 |  | Pending
| WTG 38 |  | Pending
| WTG 39 |  | Pending
| WTG 40 |  | Pending
| WTG 41 |  | Pending
| WTG 42 |  | Pending
| WTG 43 |  | Pending
| WTG 44 |  | Pending
| WTG 45 |  | Pending
| WTG 46 |  | Pending
| WTG 47 |  | Pending
| WTG 48 |  | Pending
| WTG 49 |  | Pending
| WTG 50 |  | Pending
| WTG 51 |  | Pending
| WTG 52 |  | Pending
| WTG 53 |  | Pending
| WTG 54 |  | Pending
| WTG 55 |  | Pending
| WTG 56 |  | Pending
| WTG 57 |  | Pending
| WTG 58 |  | Pending
| WTG 59 |  | Pending
| WTG 60 |  | Pending
| WTG 61 |  | Pending
| WTG 62 |  | Pending
| WTG 63 |  | Pending
| WTG 64 |  | Pending
| WTG 65 |  | Pending
| WTG 66 |  | Pending
| WTG 67 |  | Pending
| WTG 68 |  | Pending
| WTG 69 |  | Pending

## Target_Forecast (hidden)
Day | Target | Actual MV | Actual Joints
Day 1 | 2
Day 2 | 4
Day 3 | 6
Day 4 | 8
Day 5 | 10
Day 6 | 12
Day 7 | 14
Day 8 | 16
Day 9 | 18
Day 10 | 20
Day 11 | 22
Day 12 | 24
Day 13 | 26
Day 14 | 28
Day 15 | 30
Day 16 | 32
Day 17 | 34
Day 18 | 36
Day 19 | 38
Day 20 | 40
Day 21 | 42
Day 22 | 44
Day 23 | 46
Day 24 | 48
Day 25 | 50
Day 26 | 52
Day 27 | 54
Day 28 | 56
Day 29 | 58
Day 30 | 60
Day 31 | 62
Day 32 | 64
Day 33 | 66
Day 34 | 68
Day 35 | 70
Day 36 | 72
Day 37 | 74
Day 38 | 76
Day 39 | 78
Day 40 | 80
Day 41 | 82
Day 42 | 84
Day 43 | 86
Day 44 | 88
Day 45 | 90
Day 46 | 92
Day 47 | 94
Day 48 | 96
Day 49 | 98
Day 50 | 100
Day 51 | 102
Day 52 | 104
Day 53 | 106
Day 54 | 108
Day 55 | 110